## Sheet1
R1: No more than five weeks should elapse for a single sprint.
Project Name | Total Sprints | Sprint Sample Value per Project | NaNs in Sprints Start Date | NaNs in Sprints End Date | Sprint Duration (in days) - counts | Percentage | Binary Output | Comments
XD | 66 | Sprint 68 | N/A | N/A | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Apstud | 34 | 2012 Sprint 15 | N/A | N/A | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Tistud | 59 | 2012 Sprint 18 | N/A | N/A | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Mobile | 23, out of which, 1 sprint is invalid, cause it is a duplication of two individual sprints that already exist in the project. So, for this rule, only 22 sprints are analyzed in this project! | "[’com.atlassian.greenhopper.service.sprint.Sprint@245be8a[id=289,rapidViewId=43,state=ACTIVE,name=Moodle App 3.8.2,startDate=2020-03-30T11:10:08.305Z,endDate=2020-04-03T16:56:00.000Z,completeDate=<null>,activatedDate=2020-03-30T11:10:08.305Z,sequence=289,goal=]’]" | 0 | 0 | Sprint 74: 29 days 23:59:37.232000 Sprint 75: 43 days 23:59:36.097000 Sprint 79: 25 days 15:28:15.293000 Sprint 85: 7 days 13:59:31.072000 Sprint 92: 35 days 13:59:00.015000 Sprint 95: 61 days 13:59:20.498000 Sprint 106: 74 days 01:59:46.847000 Sprint 114: 58 days 01:59:28.395000 Sprint 125: 52 days 01:59:53.962000 Sprint 136: 59 days 06:45:29.153000 Sprint 143: 86 days 06:45:01.383000 Sprint 52: 12 days 06:45:58.552000 Sprint 160: 10 days 06:45:09.003000 Sprint 165: 2 days 06:45:48.239000 Sprint 167: 55 days 06:45:42.189000 Sprint 170: 54 days 06:45:26.546000 Sprint 176: 51 days 15:07:34.811000 Sprint 195: 62 days 06:46:00 Sprint 202: 66 days 15:07:34.899000 Sprint 229: 87 days 06:46:00 Sprint 264: 58 days 05:46:00 Sprint 289: 4 days 05:45:51.695000 | 6/22 sprints pass the rule (including the Sprint that lasted 29 days) 16/22 sprints fail the rule | 0 | There are 23 sprints in this project, and most of them (15/23) lasted much longer than 4 weeks. This tells us that this team was doing long sprints that exceed the principles of the Scrum Guide.
MDL | 269 | "[’com.atlassian.greenhopper.service.sprint.Sprint@40c6b8aa[id=237,rapidViewId=126,state=ACTIVE,name=Moodle 3.9 - Moppies Kanban,startDate=2019-09-15T13:49:00.000Z,endDate=2019-10-31T14:49:00.000Z,completeDate=<null>,sequence=237,goal=<null>]’]" | 1 sprint has NULL start date: <null>,endDate=<null>,co | 1 sprint has NULL end date: <null>,completeDate=<nul | Sprint 114: 58 days Sprint 114: 33 days Sprint 237: 46 days Sprint 245: 32 days Sprint 264: 58 days Sprint 92: 35 days | Total Sprints After cleaning the data field: 126 sprints Cleaning was done, due to the fact that there were may sprints with invalid IDs (combination of other sprints IDs), duplicate IDs, etc. 120/126 sprints pass the rule 6/126 sprints fail the rule since the duration of these spritns was more than 28 days | 0 | There is one sprint with NULL start and end date! Most of the sprints (120) were lasting less than 4 weeks, as prescribed by the Scrum Guide. There are only 6 sprints that lasted longer than the usual. Overall, MDL project sprints seem to have adhered to the Scrum principles as per Scrum Guide.
DNN | 103 | Sprint 2; Content 8.1.0 - Sprint 3; | N/A | N/A | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Mesos | 70 | Mesosphere Sprint 34 | N/A | N/A | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Mule | 104 | startDate=2016-04-27T11:27:32.496-05:00 | 1 sprint has no valid start date Its value is: startDate=<null> | 104. There is no end date recorded for this project. For the analysis, the start date of the next sprint will be considered as the end date of the previous sprint. | Sprint: 2015-10-19 14:50:33.528000-05:00: 42 days | 102/103 sprints pass the rule. 1/103 sprint fails the rule. Its duration is 42 days! 103 sprints in total, because we do not have information for the duration of 1 sprint. | 0 | For this project, we only have the start date. Since the end date is missing, the start date of the next sprint is considered as the end date of the previous sprint. Almost all (102/103) of the sprints in this project have a duration less than 28 days, very well aligned with Scrum Guide guidelines. Only 1 sprint has a duration of 42 days, thus failing the rule. There is one sprint with invalid date.
Nexus | 70 | Sprint 68 - Föhn | N/A | N/A | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Timob | 63 | Documentation Sprint 03 - 2016; Sprint 2012-15 API | N/A | N/A | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
R4: The duration of all sprints should follow similar pace.
Project Name | Total Sprints | NaNs in Sprints Start Date | NaNs in Sprints End Date | Sprint Duration (in days) - counts | Percentage | Binary Output | Comments
XD | 66 | N/A | N/A | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Apstud | 34 | N/A | N/A | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Tistud | 59 | N/A | N/A | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Mobile | 23, out of which, 1 sprint is invalid, cause it is a duplication of two individual sprints that already exist in the project. So, for this rule, only 22 sprints are analyzed in this project! | 0 | 0 | Sprint 74: 29 days 23:59:37.232000 Sprint 75: 43 days 23:59:36.097000 Sprint 79: 25 days 15:28:15.293000 Sprint 85: 7 days 13:59:31.072000 Sprint 92: 35 days 13:59:00.015000 Sprint 95: 61 days 13:59:20.498000 Sprint 106: 74 days 01:59:46.847000 Sprint 114: 58 days 01:59:28.395000 Sprint 125: 52 days 01:59:53.962000 Sprint 136: 59 days 06:45:29.153000 Sprint 143: 86 days 06:45:01.383000 Sprint 52: 12 days 06:45:58.552000 Sprint 160: 10 days 06:45:09.003000 Sprint 165: 2 days 06:45:48.239000 Sprint 167: 55 days 06:45:42.189000 Sprint 170: 54 days 06:45:26.546000 Sprint 176: 51 days 15:07:34.811000 Sprint 195: 62 days 06:46:00 Sprint 202: 66 days 15:07:34.899000 Sprint 229: 87 days 06:46:00 Sprint 264: 58 days 05:46:00 Sprint 289: 4 days 05:45:51.695000 | Descriptives for the sprint duration: count 1209 mean 53 days 05:19:15.071289454 std 20 days 12:15:56.771457106 min 2 days 06:45:48.239000 25% 51 days 15:07:34.811000 50% 55 days 06:45:42.189000 75% 62 days 06:46:00 max 87 days 06:46:00 9/22 sprints pass the rule (as they have similar amounts of time for completion: Sprints: 170, 95, 195, 167, 176, 264, 136, 114, 125) 14/22 sprints fail the rule, cause their duration is very widespread. | 0 | The sprints in this project were definitely not following a similar pace. As we can see from the descriptives, there are sprints that took only 2 days to complete, and there are sprints that took 87 days to comlpete. However, there are 9 sprints that took around 50 to 60 days to complete, which duration is similar.
MDL | 269 | 1 | 1 | 18 days 00:00:00 293 18 days 08:00:00 149 20 days 23:59:44.867000 129 18 days 07:59:16.554000 86 18 days 07:59:31.039000 76 18 days 08:07:00 56 15 days 07:59:44.435000 53 18 days 05:41:27.883000 52 14 days 00:00:00 49 17 days 08:21:00 49 17 days 00:00:00 49 18 days 08:19:59.001000 48 17 days 23:59:24.732000 46 20 days 11:11:10.672000 45 18 days 07:59:48.967000 44 18 days 11:59:06.843000 42 46 days 01:00:00 40 15 days 07:59:26.577000 39 21 days 23:59:01.298000 36 18 days 07:59:54.022000 33 23 days 00:00:00 32 18 days 07:59:02.189000 30 17 days 23:59:17.250000 30 18 days 07:59:26.377000 29 18 days 14:59:11.353000 29 20 days 09:54:28.441000 28 18 days 07:59:09.539000 27 10 days 23:59:00 27 18 days 23:57:00 25 20 days 05:00:00 24 17 days 07:59:50.086000 23 9 days 23:59:40.538000 22 18 days 07:59:09.324000 20 20 days 09:55:39.972000 20 32 days 00:59:51.602000 19 17 days 23:59:16.974000 19 6 days 23:59:53.615000 18 17 days 00:11:07.582000 18 18 days 05:59:06.863000 18 20 days 23:59:19.840000 17 18 days 06:59:10.857000 17 18 days 18:59:53.717000 17 18 days 06:59:38.272000 16 18 days 17:56:00 16 18 days 06:59:45.075000 15 20 days 09:55:54.378000 15 20 days 10:22:42.613000 15 20 days 23:59:43.683000 15 16 days 23:59:16.977000 15 9 days 23:59:20.469000 14 18 days 06:59:47.674000 14 13 days 23:59:49.228000 14 18 days 06:59:57.679000 14 18 days 08:54:05.709000 13 18 days 01:59:14.168000 12 18 days 03:25:31.873000 12 11 days 06:59:41.107000 12 18 days 10:03:17.695000 12 18 days 07:59:56.434000 11 17 days 17:55:36.498000 11 9 days 23:59:46.201000 11 18 days 03:25:39.663000 10 10 days 23:59:37.997000 10 14 days 23:59:38.190000 9 16 days 23:59:02.645000 9 18 days 05:00:00 9 20 days 23:59:15.623000 9 19 days 02:47:24.168000 9 17 days 01:59:49.571000 8 13 days 12:00:00 8 11 days 14:19:26.545000 8 13 days 23:59:30.015000 8 11 days 03:07:01.472000 7 18 days 13:04:27.896000 7 18 days 07:59:56.377000 7 15 days 08:25:47.855000 7 8 days 23:59:05.796000 7 17 days 23:59:59.746000 7 11 days 17:55:56.803000 6 11 days 05:59:40.210000 6 16 days 23:59:07.572000 6 20 days 23:59:41.836000 6 16 days 23:59:07.983000 6 17 days 23:59:11.825000 6 18 days 05:59:58.241000 5 13 days 23:59:49.212000 5 13 days 23:59:36.053000 4 18 days 13:59:18.422000 4 13 days 23:59:28.477000 4 10 days 23:59:28.010000 4 11 days 02:59:38.533000 4 13 days 23:59:15.247000 3 13 days 23:59:12.176000 3 13 days 23:59:01.043000 3 13 days 23:59:05.458000 3 13 days 23:59:41.952000 2 14 days 06:58:13.048000 2 9 days 23:59:32.468000 2 17 days 11:59:00 2 13 days 23:59:40.885000 2 58 days 05:46:00 1 33 days 12:19:00 1 13 days 23:59:56.002000 1 11 days 11:59:00 1 13 days 23:59:25.828000 1 13 days 23:59:49.670000 1 58 days 01:59:28.395000 1 35 days 13:59:00.015000 1 13 days 17:29:00 1 13 days 23:59:07.625000 1 | Total Sprints After cleaning the data field: 126 sprints Descriptives for the sprint duration: count 2417 mean 18 days 08:59:58.505575482 std 4 days 18:45:10.662651953 min 6 days 23:59:53.615000 25% 17 days 23:59:17.250000 50% 18 days 07:59:09.324000 75% 18 days 10:03:17.695000 max 58 days 05:46:00 12/126 sprints lasted 17 days. 3/126 sprints lasted 16 days 36/126 sprints lasted 18 days. 10/126 sprints lasted 20 days. 1/126 sprints lasted 19 days. 62/126 sprints followed a similar duration among the sprints, thus 62 sprints pass the rule 64/126 sprints have taken longer or less than the average+std time duration, thus for 64 sprints, the rule fails | 0 | Roughly half of the sprints (62/126) have followed a similar duration of completion. Additionally, there are more sprints who have taken around 13 days to complete. However, there are several sprints that interestignly have taken much longer or lesser to complete than the majority of the sprints in total.
DNN | 103 | N/A | N/A | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Mesos | 70 | N/A | N/A | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Mule | 104 | 1 | 104. There is no end date recorded for this project. For the analysis, the start date of the next sprint will be considered as the end date of the previous sprint. | Many sprints to show. Can be found in the notebook. | count 1146.000000 mean 0.967714 std 3.698909 min 0.000000 25% 0.000000 50% 0.000000 75% 0.000000 max 42.000000 20/103 sprints have shared a similar range of duration, from 0 to 3 days. 83/103 sprints have taken longer than the aforestated range of similar duration. There are 5 sprints that started instantly after the previous sprint was finished. | 0 | Most of the sprints have a similar pace of completion, time wise. However, there are around 6 sprints in this project whose completion duration deviates from the others. Only 1 sprint took 42 days to complete. All other sprints took less than 28 days. Project Mule complies to the Scrum rules well.
Nexus | 70 | N/A | N/A | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Timob | 63 | N/A | N/A | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
R5: The next Sprint execution should begin only after the previous Sprint's resolution.
Project Name | Total Sprints | Sprint Duration (in days) - count | Percentage | Binary Output | Comments
XD | 66 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Apstud | 34 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Tistud | 59 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Mobile | 23, out of which, 1 sprint is invalid, cause it is a duplication of two individual sprints that already exist in the project. So, for this rule, only 22 sprints are analyzed in this project! | Sprint 170: 54 days 06:45:26.546000 Sprint 95: 61 days 13:59:20.498000 Sprint 195: 62 days 06:46:00 Sprint 229: 87 days 06:46:00 Sprint 167: 55 days 06:45:42.189000 Sprint 92: 35 days 13:59:00.015000 Sprint 85: 7 days 13:59:31.072000 Sprint 106: 74 days 01:59:46.847000 Sprint 176: 51 days 15:07:34.811000 Sprint 202: 66 days 15:07:34.899000 Sprint 264: 58 days 05:46:00 Sprint 74: 29 days 23:59:37.232000 Sprint 136: 59 days 06:45:29.153000 Sprint 79: 25 days 15:28:15.293000 Sprint 114: 58 days 01:59:28.395000 Sprint 165: 2 days 06:45:48.239000 Sprint 125: 52 days 01:59:53.962000 Sprint 143: 86 days 06:45:01.383000 Sprint 75: 43 days 23:59:36.097000 Sprint 289: 4 days 05:45:51.695000 Sprint 152: 12 days 06:45:58.552000 Sprint 160: 10 days 06:45:09.003000 | 21/22 sprints pass the rule 1/22 sprints fail the rule | 0 | 22 sprints in this project begin after the previous sprint has already been completed. There is one sprint that has started before the previous sprint has been finished. This can be due to the fact that Jira has not recorded all sprints for this project and there can be sprints in between whose data we do not have!
MDL | 269 | Many sprints to show. Can be found in the notebook. | 38/126 sprints pass the rule 43/126 sprints fail the rule For the remaining 45/126 sprints, we can't calculate this information because there are missing sprints between them. For example, we have a sprint with id: 150, but we do not have both Sprint 149 nor Sprint 151. | 0 | 59 sprints fail the rule. Whereas for 67 other sprints, they have started after the previous sprint has been comlpeted.
DNN | 103 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Mesos | 70 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Mule | 104 | Many sprints to show. Can be found in the notebook. | 103/104 sprints pass for this rule. For 1/104 sprint, we do not have the information. | 1 | All sprints in this project begin after the previous sprint has been closed. From the results, I observe that the sprints were shorter and the team accommodated usually 2 sprints per month, sometimes 1 and sometimes more. Once again, Mule project complies with the rules very well.
Nexus | 70 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Timob | 63 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
R6: There should be a project clarity identifier attached to each issue within the sprints.
Project Name | Total Issues | Total Sprints | Empty Project Clarity IDs | Percentage (Issues Unit) | Binary Output | Comments
XD | 3152 | 66 | 0 | 66/66 sprints pass the rule | 1 | In all 66 sprints, all issues have a valid Project ID/Name
Apstud | 825 | 34 | 0 | 34/34 sprints pass the rule | 1 | In all 34 sprints, all issues have a valid Project ID/Name
Tistud | 2826 | 59 | 0 | 59/59 sprints pass the rule | 1 | In all 59 sprints, all issues have a valid Project ID/Name
Mobile | 3242 | 23 | 0 | 23/23 sprints pass the rule | 1 | In all 23 sprints, all issues have a valid Project ID/Name
MDL | 63273 | 269 | 0 | 269/269 sprints pass the rule | 1 | In all 269 sprints, all issues have a valid Project ID/Name
DNN | 1874 | 103 | 0 | 103/103 sprints pass the rule | 1 | In all 103 sprints, all issues have a valid Project ID/Name
Mesos | 1365 | 70 | 0 | 70/70 sprints pass the rule | 1 | In all 70 sprints, all issues have a valid Project ID/Name
Mule | 1278 | 104 | 0 | 104/104 sprints pass the rule | 1 | In all 104 sprints, all issues have a valid Project ID/Name
Nexus | 1037 | 70 | 0 | 70/70 sprints pass the rule | 1 | In all 70 sprints, all issues have a valid Project ID/Name
Timob | 1853 | 63 | 0 | 63/63 sprints pass the rule | 1 | In all 63 sprints, all issues have a valid Project ID/Name
R7: No considerable amount of time should elapse between the finish of a sprint and the beginning of the new sprint. Scrum Guide uses the word: "immediately". We will consider a one week gap between sprints, letting enough time to prepare the SPB.
Project Name | Total Sprints | Sprints Time Differences (between finish of first sprint and beginning of next sprint) | Percentage | Binary Output | Comments
XD | 66 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Apstud | 34 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Tistud | 59 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Mobile | 23, out of which, 1 sprint is invalid, cause it is a duplication of two individual sprints that already exist in the project. So, for this rule, only 22 sprints are analyzed in this project! | 5.0 2 14.0 2 17.0 2 24.0 1 12.0 1 -22.0 1 16.0 1 81.0 1 13.0 1 2.0 1 39.0 1 4.0 1 6.0 1 49.0 1 45.0 1 8.0 1 77.0 1 10.0 1 -30.0 1 | 6/22 sprints pass the rule 16/22 rules fail the rule (out of 16, 1 sprint has started before the previous sprint has been completed) | 0 | As we can see, between some sprints, the time between the finish of the first and beginning of the next sprint is 2 days, 4 days. But in other cases, this difference goes really high, more than 81 days!
MDL | 269 | 2.0 20 9.0 13 -19.0 13 -14.0 12 -18.0 8 0.0 8 -1.0 5 3.0 5 -11.0 3 -8.0 2 -17.0 2 -10.0 2 -4.0 2 -13.0 2 -5.0 1 -12.0 1 48.0 1 -32.0 1 -39.0 1 -9.0 1 23.0 1 -16.0 1 12.0 1 65.0 1 38.0 1 58.0 1 -15.0 1 215.0 1 -21.0 1 11.0 1 93.0 1 187.0 1 -51.0 1 46.0 1 30.0 1 14.0 1 -7.0 1 -2.0 1 44.0 1 37.0 1 6.0 1 1.0 1 -45.0 1 | count 126.000000 mean 1.150794 std 32.151657 min -51.000000 25% -14.000000 50% -0.500000 75% 3.000000 max 215.000000 24/126 sprints pass the rule 60/126 sprints fail the rule There are only 84 consecutive sprints, as per the SPRINT_ID column, extracted from SPRINT original data field. The other sprints do not have a previous or next sprint information recorded. | 0 | There are 265 sprints in total, but there are missing sprint between them. There are only 84 consecutive sprints, upon which we can check this rule. Out of them, only 24 sprints have recorded less than a week from its completion date untilt the next sprint has started. In 60 sprints in this project, there have been delays more than 1 week between current sprint's resolution date and the next sprint's beginning date. We can conclude that in order to have more accurate insights for this rule for this project, we need to have the information for all sprints within the project.
DNN | 103 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Mesos | 70 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Mule | 104 | Can be seen from notebook. A lot of information to fit in this cell. | 28/103 sprints pass the rule 75/103 sprints fail the rule | 0 | 28 sprints out of the 103 valid sprints, have started within the next 6 days after the previous sprint has been concluded. However, the major part of sprints in Mule project have taken more than 6 days, or as Scrum Guide suggests: "immediately", to start after the previous ones have been completed.
Nexus | 70 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Timob | 63 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
R8: There should not be a considerable amount of time for a developer to volunteer and start a new issue after she/he has completed the previous one per each sprint.
Project Name | Total Sprints | Total Issues | Sprints that fail the rule | Percentage | Binary Output | Comments
XD | 66 | 3152 | Sprint 12: 28 days idle for all developers in total Sprint 15: 7 days idle for all developers in total Sprint 16: 8 days idle for all developers in total Sprint 18: 13 days idle for all developers in total Sprint 19: 11 days idle for all developers in total Sprint 21: 26 days idle for all developers in total Sprint 22: 18 days idle for all developers in total Sprint 24: 29 days idle for all developers in total Sprint 27: 29 days idle for all developers in total sprint 28: 5 days idle for all developers in total Sprint 30: 22 days idle for all developers in total Sprint 31: 27 days idle for all developers in total Sprint 32: 3 days idle for all developers in total Sprint 35: 9 days idle for all developers in total Sprint 38: 8 days idle for all developers in total Sprint 41: 16 days idle for all developers in total Sprint 42: 3 days idle for all developers in total Sprint 44: 5 days idle for all developers in total Sprint 49: 7 days idle for all developers in total Sprint 50: 12 days idle for all developers in total Sprint 54: 6 days idle for all developers in total Sprint 55: 10 days idle for all developers in total Sprint 56: 3 days idle for all developers in total Sprint 57: 7 days idle for all developers in total Speint 60: 8 days idle for all developers in total Sprint 61: 19 days idle for all developers in total | 40/66 sprints pass the rule 26/66 sprints fail the rule | 0 | For each developer in each sprint of the project, their idle time has been calculated and added up with the idle time of other developers who contributed in that sprint. As we can see, in 26 sprints out of 66, developers have been idle for unreasonable amount of times. The Scrum Guide states that the developers should volunteer for another task after they are done completing the current task. This rule shows that in XD project, developers have not started working for new tasks after completing the previous ones, rather, they have been waiting more than necessary. Reasons behind this might be that there were not enough tasks at the time of the sprint, or that the developers finished faster the previous tasks assigned to them.
Apstud | 34 | 825 | 2012 Sprint 04, 2012 Sprint 06, 2012 Sprint 08, 2012 Sprint 12, 2012 Sprint 13 | 29/34 sprints pass the rule 5/34 sprints fail the rule | 0 | Only in 5 sprints, the developers have been idle for a non-reasonable amount of time (2 days).
Tistud | 59 | 2826 | 2012 Sprint 02, 2012 Sprint 04, 2012 Sprint 05, 2012 Sprint 05, 2012 Sprint 07, 2012 Sprint 09, 2012 Sprint 12, 2012 Sprint 15, 2012 Sprint 16, 2012 Sprint 19, 2012 Sprint 20, 2012 Sprint 21, 2012 Sprint 22, 2013 Sprint 02, 2013 Sprint 07 2013 Sprint 08 2013 Sprint 10 2013 Sprint 11, 2013 Sprint 12, 2013 Sprint 13, 2013 Sprint 17, 2013 Sprint 19, 2013 Sprint 22, 2013 Sprint 23, 2013 Sprint 24, 2013 Sprint 25, 2013 Sprint 26, 2014 Sprint 01 2014 Sprint 02 | 30/59 sprints pass the rule 29/59 sprints fail the rule | 0 | In roughly half of the sprints, developers have recorded longer waiting times than 2 days
Mobile | 23 | 3242 | 1. Sprint 167, 2. Sprint 85, 3. Sprint 170, 4. Sprint 79, 5. Sprint 92, 6. Sprint 176, 7. Sprint 75, 8. Sprint 229, 9. Sprint 95, 10. Sprint 74, | 13/23 sprints pass the rule 10/23 sprints fail the rule | 0 | In 10 sprints out of 23, developers have been waiting to work on new tasks during the sprint.
MDL | 269 | 63273 | Sprint 70, Sprint 22, Sprint 105, Sprint 132, Sprint 21, Sprint 31, Sprint 76, Sprint 8, Sprint 7, Sprint 41, Sprint 10, Sprint 14, Sprint 159, Sprint 50, Sprint 48, Sprint 168, Sprint 4, Sprint 30, Sprint 18, Sprint 59, Sprint 72, | 248/269 sprints pass the rule 21/269 sprints fail the rule | 0 | In 21 sprints out of 269, developers have been waiting for more than 2 days to work on a new issue after completing the previous one.
DNN | 103 | 1874 | 1. 3.0 - Sprint 2 2. 3.0 - Sprint 3 3. 7.2.1 Sprint 3 4. 7.2.2 Sprint 2 5. 7.3.0 Sprint 2 6. 7.3.0 Sprint 4 7. 7.3.0 Sprint 5 8. 7.3.2 Sprint 3 9. 8.0.0 - Sprint 6 10. 8.0.0 - Sprint 8 11. Content 8.1.0 - Sprint 6 (FF) 12. Platform 8.0 - Sprint 10 QA 13. Platform 8.0 - Sprint 11' 14. Platform 8.0 - Sprint 12 15. Platform 8.0 - Sprint 13' 16. Platform 8.0 - Sprint 15 (FF) 17. Platform 8.0.1 - Sprint 2 18. Platform 8.1 - Sprint 1 19. Platform 8.1 - Sprint 2 | 84/103 sprints pass the rule 19/103 sprints fail the rule | 0 | In most of the sprints, the develoeprs did not log any long idle time while working on issues of the sprint.
Mesos | 70 | 1365 | 1. Mesos Q3 Sprint 6 2. Mesosphere Sprint 19 3. Mesosphere Sprint 21 4. Mesosphere Sprint 23 5. Mesosphere Sprint 24 6. Mesosphere Sprint 27 7. Mesosphere Sprint 31 8. Q3 Sprint 2 9. Twitter Mesos Q1 Sprint 4 10. Twitter Mesos Q2 Sprint 5 11. Twitter Mesos Q3 Sprint 2 12. Twitter Mesos Q3 Sprint 3' 13. Twitter Mesos Q3 Sprint 5 14. Twitter Q2 Sprint 2 15. Twitter Q2 Sprint 3 | 55/70 sprints pass the rule 15/70 sprints fail the rule | 0 | In most of the sprints, the develoeprs did not log any long idle time while working on issues of the sprint.
Mule | 104 | 1278 | 1. startDate=2013-03-20T10:30:40.323-05:00 2. startDate=2013-05-22T16:15:45.928-05:00 3. startDate=2013-11-11T11:43:35.237-06:00 4. startDate=2014-01-15T12:46:01.433-06:00 5. startDate=2014-01-29T11:36:32.807-06:00 6. startDate=2014-02-12T12:23:10.713-06:00 7. startDate=2014-02-26T11:51:46.561-06:00 8. startDate=2014-03-12T13:52:05.072-05:00 9. startDate=2014-03-27T11:30:16.560-05:00 10. startDate=2014-04-09T11:55:24.970-05:00 11. startDate=2014-04-23T15:36:05.772-05:00 12. startDate=2014-05-21T12:21:28.801-05:00 13. startDate=2014-06-04T11:17:30.212-05:00 14. startDate=2014-07-03T12:37:05.770-05:00 15. startDate=2014-08-29T12:23:23.852-05:00 16. startDate=2014-09-30T12:20:00.000-05:00 17. startDate=2014-11-06T12:39:28.945-06:00 18. startDate=2014-11-20T12:24:09.617-06:00 19. startDate=2014-12-04T12:35:13.367-06:00 20. startDate=2014-12-18T12:02:13.591-06:00 21. startDate=2015-01-09T14:00:22.595-06:00 22. startDate=2015-01-22T12:52:49.506-06:00 23. startDate=2015-03-05T12:25:47.308-06:00 24. startDate=2015-03-20T13:59:51.264-05:00 25. startDate=2015-04-09T10:59:36.335-05:00 26. startDate=2015-04-23T13:27:13.198-05:00 27. startDate=2015-05-07T12:32:44.848-05:00 28. startDate=2015-06-04T11:29:52.897-05:00 29. startDate=2015-07-16T11:41:49.636-05:00 30. startDate=2015-08-25T10:54:24.300-05:00 31. startDate=2015-11-05T10:48:06.531-06:00 32. startDate=2015-12-03T10:46:30.826-06:00 33. startDate=2016-01-07T09:09:52.401-06:00 34. startDate=2016-02-04T20:59:53.373-06:00 35. startDate=2016-02-29T09:42:26.488-06:00 36. startDate=2016-04-27T11:27:32.496-05:00 | 68/104 sprints pass the rule 36/104 sprints fail the rule | 0 | In most of the sprints, the develoeprs did not log any long idle time while working on issues of the sprint.
Nexus | 70 | 1037 | 1. Sprint 44 2. Sprint 45 | 68/70 sprints pass the rule 2/70 sprints fail the rule | 0 | Almost in all sprints, the developers did not wait between undertaking issues. Nexus project complies well with this rule.
Timob | 63 | 1853 | 0 | All 63 sprints pass the rule | 1 | All sprints in this project pass the rule. Developers did not log waiting times while completing their tasks within the sprints. A reason behind these results can be that despite there being 63 sprints in this project, most of the issues have not been linked to their corresponding sprints. Or, it can be the case that this project was not using sprints for development.
R24: The backlog does not contain meaningless or empty issues. I consider meaningless issues the issues that are duplicate, belong to no project and have no issue body, description and other details that are relevant to developers and other roles for completing them.
Project Name | NaNs in Sprint Field | NaNs in Description | NaNs in Summary | NaNs in Priority | NaNs in Issue Status | NaNs in Story Points | Percentage (Issue Unit) | Binary Output | Comments
XD | 1326 | 0 | 0 | 0 | 0 | 0 | 3152/3152 issues pass the rule | 1 | assignee.name has 933 null values resolutiondate has 574 null values sprint has 1326 null values
Apstud | 410 | 0 | 0 | 0 | 0 | 0 | 825/825 issues pass the rule | 1 | resolutiondate has 237 null values sprint has 410 null values
Tistud | 1089 | 0 | 0 | 1/2826 Issue: 'TISTUD-6753' has no priority assigned to it. It also belongs to no sprint! | 0 | 6 TISTUD-8447, TISTUD-8027, TISTUD-8022, TISTUD-8021, TISTUD-7999, TISTUD-7984 are the only 6 issues that do not have story points assigned to out of all other issues. Since there are only 6 issues that do not have story points, and all others have this information, it means that these 6 issues do not carry the full information as the majority of the other issues. Same goes for the 1 issue that does not have a priority label attached to it. | 2819/2826 issues pass the rule 7/2826 issues fail the rule | 0 | priority.name has 1 null values resolutiondate has 198 null values storypoints has 6 null values sprint has 1089 null values
Mobile | 2032 | 0 | 0 | 0 | 0 | 3242/3242 All issues do not have story points, which means that this practice is not used in the Mobile Project. Therefore, this number of NaNs will not affect the analysis of this project. | 3242/3242 issues pass the rule | 1 | assignee.name has 520 null values resolutiondate has 359 null values storypoints has 3242 null values sprint has 2032 null values
MDL | 60540 | 0 | 0 | 0 | 0 | 61871/63273 issues do not have story points assigned to them. This means that MDL project did not use any practice related to story points. However, it is worth mentioning that a small number of issues (1402) actually have story points assigned. It could be that they tried to incorporate some story points practice in the beginning or along the way, but it did not turn out to be useful for them, hence they stopped. | 63271/63273 issues pass the rule 2/63273 issues fail the rule Out of these 4 issues, 3 of them do not have a reporter, and one of them, does not have an Issue ID/Name. | 0 | assignee.name has 16919 null values reporter.name has 3 null values resolutiondate has 10285 null values key has 1 null values storypoints has 61871 null values sprint has 60540 null values
DNN | 246 | 0 | 0 | 0 | 0 | 0 | 1874/1874 pass the rule | 1 | assignee.name has 1002 null values resolutiondate has 104 null values sprint has 246 null values This project has 40 incomplete issues per sprints!
Mesos | 286 | 0 | 0 | 0 | 0 | 0 | 1365/1365 issues pass the rule | 1 | assignee.name has 119 null values resolutiondate has 277 null values sprint has 286 null values This project has the most incomplete issues per sprints (103 issues)!
Mule | 120 | 0 | 0 | 0 | 0 | 0 | 1278/1278 issues pass the rule | 1 | assignee.name has 55 null values resolutiondate has 78 null values sprint has 120 null values
Nexus | 404 | 0 | 0 | 0 | 0 | 0 | 1034/1037 pass the rule 3/1037 issues fail the rule. There are 3 issues in this project that do not have a reporter! This is an interesting catch, since by default, Jira records as reporters, the person who creates the issue. What does this mean in the case of these 3 issues? How and who created them? | 0 | assignee.name has 287 null values reporter.name has 3 null values resolutiondate has 42 null values sprint has 404 null values
Timob | 1574 | 0 | 0 | 1 Issue: TIMOB-17705 has no priority assigned to it. It also belongs to no sprint! | 0 | 0 | 1852/1853 issues pass the rule 1/1853 fails the rule Since there is only 1 issue that does not have priority label, and all other issues have this information, it means that this 1 issue does not carry the full information as the majority of the other issues. | 0 | priority.name has 1 null values resolutiondate has 174 null values sprint has 1574 null values
R27: No more than 8 active developers should be involved in development tasks
Project Name | Total Issues Before and After Retaining only Active Developers | Total Sprints Before and After Retaining only Active Developers | Total Developers Before and After Retaining only Active Developers | Threshold <= | Active Developers | Percentage (Sprint Unit) | Binary Output | Comments
XD | Before: 3152 After:2566 | Before: 66 After: 66 | Before: 31 After: 8 | 98 | 1 to 9 devs per sprint | 66/66 sprints pass the rule | 1 | Out of 3152 issues, 2219 of them have developers assigned to them.
Apstud | Before: 825 After: 646 | Before: 34 After: 34 | Before: 11 After: 4 | 59 | 1-4 devs per sprint | 34/34 sprints pass | 1 | Out of 825 issues, 825 of them have developers assigned to them.
Tistud | Before: 2826 After: 2494 | Before: 59 After: 59 | Before: 31 After: 5 | 100 | 2-5 devs per sprint | 59/59 sprints pass | 1 | Out of 2826 issues, 2826 of them have developers assigned to them.
Mobile | Before: 3242 After: 2789 | Before: 23 After: 23 | Before: 28 After: 3 | 100 | 1-3 devs per sprint | 23/23 sprints pass | 1 | Out of 3242 issues, 2722 of them have developers assigned to them.
MDL | Before: 63273 After: 50108 | Before: 269 After: 165 | Before: 522 After: 23 | 386 | 1-7 devs per sprint. 25 sprints have 0 developers in them. 1 sprint has 10 active devs. | 139/165 sprints pass 26/165 sprints fail | 0 | Out of 63273 issues, 46354 of them have developers assigned to them. ------------ 25 sprints have 0 developers in them. 1 sprint has 10 active devs.
DNN | Before: 1874 After: 1860 | Before: 103 After: 100 | Before: 12 After: 6 | 62 | 1-6 devs per sprint 9 sprints have 0 developers | 91/100 sprints pass 9/100 sprints fail | 0 - cause 9 sprints fail | Out of 1874 issues, 872 of them have developers assigned to them.
Mesos | Before: 1365 After: 821 | Before: 70 After: 65 | Before: 74. After: 13 | 31 - difficult to set a threshold for this project | 1-12 devs per sprint 1 sprint has 0 developers. 7 sprints have more than 8 active developers. | 56/65 (after) pass 8/65 fail | 0 | Out of 1365 issues, 1246 of them have developers assigned to them.
Mule | Before: 1278 After: 1014 | Before:104 After: 94 | Before: 38 After: 7 | 73 | 1-6 devs per sprint | 84/94 sprints pass 10/94 fail | 0 | Out of 1278 issues, 1223 of them have developers assigned to them.
Nexus | Before: 1037 After: 777 | Before: 70 After: 69 | Before: 22 After: 4 | 56 | 1-4 devs per sprint 8 sprints have 0 developers | 61/69 sprints pass 8/69 fail | 0 | Out of 1037 issues, 750 of them have developers assigned to them.
Timob | Before:1853 After: 1359 | Before: 63 After: 36 | Before: 49 After: 10 | 73 | 1-2 devs per sprint | 36/36 sprints pass | 1 | Out of 1853 issues, 1853 of them have developers assigned to them.
R28: The status of issues should always follow the agreed workflow, depending on the project and development team. Can check this with Apromore!
Project Name | Total Sprints | Total Issues | Total Incomplete Issues | Total Issue Statuses per Project | Statuses and their counts | Statuses (name and id) | Percentage (Sprint Unit) | Binary Output | Comments
XD | 66 | 3152 | 3152-574 | 4 | Done 2578 To Do 550 In Progress 20 In PR 4 | To Do 10000 In PR 10006 Done 10001 In Progress 3 | TODO | TODO | TODO
Apstud | 34 | 825 |  | 5 | Closed 567 Open 220 Resolved 21 Reopened 16 In Review 1 |  | TODO | TODO | TODO
Tistud | 59 | 2826 |  | 6 | Closed 2341 Resolved 287 Open 170 Reopened 22 In Progress 4 In Review 2 |  | TODO | TODO | TODO
Mobile | 23 | 3242 |  | 8 | Closed 2252 Resolved 631 Open 335 Development in progress 14 Reopened 5 Waiting for peer review 2 Waiting for testing 2 Waiting for integration review 1 |  | TODO | TODO | TODO
MDL | 269 | 63273 |  | 10 | Closed 52988 Open 9270 Reopened 492 Development in progress 361 Waiting for peer review 84 Waiting for integration review 32 Peer review in progress 30 Tested 9 Integration review in progress 6 Waiting for testing 2 |  | TODO | TODO | TODO
DNN | 103 | 1874 |  | 6 | Closed 1765 Open 76 Reopened 23 Pull Request Submitted 6 Planned Development 3 Resolved 1 |  | TODO | TODO | TODO
Mesos | 70 | 1365 |  | 5 | Resolved 1088 Accepted 136 Reviewable 65 Open 56 In Progress 20 |  | TODO | TODO | TODO
Mule | 104 | 1278 |  | 5 | Closed 1196 To Do 69 In Progress 7 Resolved 4 Reopened 2 |  | TODO | TODO | TODO
Nexus | 70 | 1037 |  | 5 | Closed 967 Open 40 Done 28 Refine 1 Raw 1 |  | TODO | TODO | TODO
Timob | 63 | 1853 |  | 5 | Closed 967 Open 40 Done 28 Refine 1 Raw 1 |  | TODO | TODO | TODO
R30: No previously resolved issue should reappear in a future sprint. Can check this with Apromore!
Project Name | Total Sprints | Total Issues | Total Resolved Issues (removing incomplete issues) | Total Reappearing Issues | Percentage (Sprint Unit) | Binary Output | Comments
XD | 66 | 3152 |  | TODO | TODO | TODO | TODO
Apstud | 34 | 825 |  | TODO | TODO | TODO | TODO
Tistud | 59 | 2826 |  | TODO | TODO | TODO | TODO
Mobile | 23 | 3242 |  | TODO | TODO | TODO | TODO
MDL | 269 | 63273 |  | TODO | TODO | TODO | TODO
DNN | 103 | 1874 |  | TODO | TODO | TODO | TODO
Mesos | 70 | 1365 |  | TODO | TODO | TODO | TODO
Mule | 104 | 1278 |  | TODO | TODO | TODO | TODO
Nexus | 70 | 1037 |  | TODO | TODO | TODO | TODO
Timob | 63 | 1853 |  | TODO | TODO | TODO | TODO
R31 - Each Scrum Sprints can be considered a short project, therefore there should be a unique identifier/name associated with each Sprint
Project Name | Total Sprints | Total Issues | NaNs - Sprint | Not Null - Sprints | Percentage (Sprint Unit) | Binary Output | Comments
XD | 66 | 3152 | 1326 | 1826 | 66/66 sprints pass pass the rule | 1 | All 66 sprints are uniquely identified
Apstud | 34 | 825 | 410 | 415 | 34/34 sprints pass pass the rule | 1 | Number of unique sprints (excluding the nan) in the Open-Source Project: 34
Tistud | 59 | 2826 | 1089 | 1737 | 59/59 sprints pass pass the rule | 1 | Number of unique sprints (excluding the nan) in the Open-Source Project: 59
Mobile | 23 | 3242 | 2032 | 1210 | 23/23 sprints pass the rule | 1 | Number of unique sprints (excluding the nan) in the Open-Source Project: 23
MDL | 269 | 63273 | 60540 | 2734 | 96% of issues do not belong to any of the 269 sprints. This is a big difference, and it is an indicator that MDL project was not working with sprints for development. Moreover, the data recorded for the sprint data field in this project is not clear. There are cases where there are multiple sprint IDs per one record. We do not know which ID is correct for the given sprint, and we can't also remove the entire row altogether, because then we lose information about many sprints. All 269 sprints are uniquely identified, but we do not have clear data as compared to most of the other projects. The rule techncially passes for this project, as all sprints are uniquely identified. | 1 | Number of unique sprints (excluding the nan) in the Open-Source Project: 269
DNN | 103 | 1874 | 246 | 1628 | 103/103 sprints pass the rule | 1 | Number of unique sprints (excluding the nan) in the Open-Source Project: 103 All of the 103 sprints are uniquely identified. However, there are issues that do not belong to any of these sprints, and the value reflected in the sprint field for those issues is NaN.
Mesos | 70 | 1365 | 286 | 1079 | 70/70 sprints pass the rule | 1 | Number of unique sprints (excluding the nan) in the Open-Source Project: 70 All of the 70 sprints are uniquely identified. However, there are issues that do not belong to any of these sprints, and the value reflected in the sprint field for those issues is NaN.
Mule | 104 | 1278 | 120 | 1158 | 103/104 sprints pass the rule 1/104 sprints fails the rule Even though we do not have information about sprints name/id, we do have information about the unique start date of the sprint, which we can use as sprint ID/Name. However, there is 1 sprint which does not have a valid start date. | 0 | Number of unique sprints (excluding the nan) in the Open-Source Project: 104 None from the 104 sprints is uniquely identified. One sprint out of 104 does not have a valid value. Also, there are issues that do not belong to any of these sprints, and the value reflected in the sprint field for those issues is NaN.
Nexus | 70 | 1037 | 404 | 633 | 70/70 sprints pass the rule | 1 | Number of unique sprints (excluding the nan) in the Open-Source Project: 70 All of the 70 sprints are uniquely identified. However, there are issues that do not belong to any of these sprints, and the value reflected in the sprint field for those issues is NaN.
Timob | 63 | 1853 | 1574 | 279 | 63/63 sprints pass the rule | 1 | Number of unique sprints (excluding the nan) in the Open-Source Project: 63 All of the 63 sprints are uniquely identified. However, there are issues that do not belong to any of these sprints, and the value reflected in the sprint field for those issues is NaN.
R32 - There should be a type, such as bug, improvement or task, associated to each issue
Project Name | Total Issues | Types | Types Values and their Count | Issues having no type | Percentage (Issues Unit) | Binary Output | Comments
XD | 3152 | 5 | Story, Bug, Improvement, Technical task, Epic | 0 | 3152/3152 issues pass pass the rule | 1
Apstud | 825 | 6 | Bug, Story, Improvement,Technical task, Epic, New Feature | 0 | 825/825 issues pass pass the rule | 1
Tistud | 2826 | 6 | Bug, Story, Improvement,Technical task, New Feature, Sub-Task | 0 | 2826/2826 issues pass pass the rule | 1 | There are 2826 values present in the issuetype.name data field. Total number of issues having no issue status is: 0.
Mobile | 3242 | 8 | Bug, Improvement, Sub-task, New Feature, Task, Epic, Story, Release Test | 0 | 3242/3242 issues pass pass the rule | 1 | There are 3242 values present in the issuetype.name data field. Total number of issues having no issue status is: 0.
MDL | 63273 | 6 | Bug 39732 Improvement 12343 Sub-task 4523 New Feature 3872 Task 2537 Epic 267 | 0 | 63273/63273 issues pass the rule | 1 | There are 63274 values present in the issuetype.name data field. Total number of issues having no issue status is: 0.
DNN | 1874 | 6 | Bug, Improvement, Story, Sub-task , Task, New Feature | 0 | 1874/1874 issues pass the rule | 1 | Total number of issue statuses present in this Open-Source Project is: 6. There are 1874 values present in the issuetype.name data field. Total number of issues having no issue status is: 0.
Mesos | 1365 | 7 | Bug 497 Task 408 Improvement 353 Documentation 74 Story 20 Epic 9 Wish 4 | 0 | 1365/1365 issues pass the rule | 1 | There are 1365 values present in the issuetype.name data field. Total number of issues having no issue status is: 0.
Mule | 1278 | 8 | Bug 594 Task 274 Improvement 251 New Feature 121 Story 32 Patch submission 2 Sub-task 2 Epic 2 | 0 | 1278/1278 issues pass the rule | 1 | Total number of issue statuses present in this Open-Source Project is: 8. There are 1278 values present in the issuetype.name data field. Total number of issues having no issue status is: 0.
Nexus | 1037 | 5 | Bug 697 Improvement 277 Story 30 Task 25 Technical Debt 8 | 0 | 1037/1037 issues pass the rule | 1 | There are 1037 values present in the issuetype.name data field. Total number of issues having no issue status is: 0.
Timob | 1853 | 7 | Bug 1141 Improvement 262 Story 218 New Feature 192 Sub-task 19 Epic 17 Technical task 4 | 0 | 1853/1853 issues pass the rule | 1 | There are 1853 values present in the issuetype.name data field. Total number of issues having no issue status is: 0.
R33 - Each issue belongs to a specific Sprint, therefore there should be a sprint identifier attached to each issue.
Project Name | Total Issues | Total Sprints | Issues Having No Sprint ID | Percentage (Issues Unit) | Binary Output | Comments
XD | 3152 | 66 | 1326 | 1826/3152 issues pass the rule 1326/3152 issues fail the rule | 0 | Total number of unique sprints present in this Open-Source Project is: 66. Total number of missing sprints present in this Open-Source Project is: 1326. Total number of unique issues present in this Open-Source Project is: 3152. Total number of missing issues present in this Open-Source Project is: 0.
Apstud | 825 | 34 | 410 | 415/825 issues pass the rule 410/825 issues fail the rule | 0 | Total number of unique sprints present in this Open-Source Project is: 34. Total number of missing sprints present in this Open-Source Project is: 410. Total number of unique issues present in this Open-Source Project is: 825. Total number of missing issues present in this Open-Source Project is: 0.
Tistud | 2826 | 59 | 1089 | 1737/2826 issues pass the rule 1089/2826 issues fail the rule | 0 | Total number of unique sprints present in this Open-Source Project is: 59. Total number of missing sprints present in this Open-Source Project is: 1089. Total number of unique issues present in this Open-Source Project is: 2826. Total number of missing issues present in this Open-Source Project is: 0.
Mobile | 3242 | 23 | 2032 | 1210/3242 issues pass the rule 2032/3242 issues fail the rule | 0 | Total number of unique sprints present in this Open-Source Project is: 23. Total number of missing sprints present in this Open-Source Project is: 2032. Total number of unique issues present in this Open-Source Project is: 3242. Total number of missing issues present in this Open-Source Project is: 0.
MDL | 63273 | 269 | 60539 | 2734/63273 issues pass the rule 60539/63273 issues fail the rule | 0 | Total number of unique sprints present in this Open-Source Project is: 269. Total number of missing sprints present in this Open-Source Project is: 60540. Total number of unique issues present in this Open-Source Project is: 63273. Total number of missing issues present in this Open-Source Project is: 1.
DNN | 1874 | 103 | 246 | 1628/1874 issues pass the rule 246/1874 issues fail the rule | 0 | Total number of unique sprints present in this Open-Source Project is: 103. Total number of missing sprints present in this Open-Source Project is: 246. Total number of unique issues present in this Open-Source Project is: 1874. Total number of missing issues present in this Open-Source Project is: 0.
Mesos | 1365 | 70 | 286 | 1079/1365 issues pass the rule 286/1365 issues fail the rule | 0 | Total number of unique sprints present in this Open-Source Project is: 70. Total number of missing sprints present in this Open-Source Project is: 286. Total number of unique issues present in this Open-Source Project is: 1365. Total number of missing issues present in this Open-Source Project is: 0.
Mule | 1278 | 104 | 120 | 1167/1287 issues pass the rule, out of which: 11/1167 issues have no valid value in the sprint field 120/1287 issues fail the rule | 0 | Total number of unique sprints present in this Open-Source Project is: 104. Total number of missing sprints present in this Open-Source Project is: 120. Total number of unique issues present in this Open-Source Project is: 1278. Total number of missing issues present in this Open-Source Project is: 0.
Nexus | 1037 | 70 | 404 | 633/1037 issues pass the rule 404/1037 issues fail the rule | 0 | Total number of unique sprints present in this Open-Source Project is: 70. Total number of missing sprints present in this Open-Source Project is: 404. Total number of unique issues present in this Open-Source Project is: 1037. Total number of missing issues present in this Open-Source Project is: 0.
Timob | 1853 | 63 | 1574 | 279/1853 issues pass the rule 1574/1853 issues fail the rule | 0 | Total number of unique sprints present in this Open-Source Project is: 63. Total number of missing sprints present in this Open-Source Project is: 1574. Total number of unique issues present in this Open-Source Project is: 1853. Total number of missing issues present in this Open-Source Project is: 0. Total number of issues belonging to no sprints is: 1574. The results indicate that the Timob project was not a fan of Sprints, since they did not incorporate Sprints in their agile work that much.
R34 - All issues must be uniquely identifiable, therefore there should be a unique identifier associated with each issue.
Project Name | Total Issues | Total Sprints | Empty issue IDs/keys | Percentage (Issues Unit) | Binary Output | Comments
XD | 3152 | 66 | 0 | 3152/3152 issues pass the rule | 1 | Total number of unique issues present in this Open-Source Project is: 3152. Total number of issues having no issue IDs in this Open-Source Project is: 0.
Apstud | 825 | 34 | 0 | 825/825 issues pass the rule | 1 | Total number of unique issues present in this Open-Source Project is: 825. Total number of missing issues present in this Open-Source Project is: 0.
Tistud | 2826 | 59 | 0 | 2826/2826 issues pass the rule | 1 | Total number of unique issues present in this Open-Source Project is: 2826. Total number of missing issues present in this Open-Source Project is: 0.
Mobile | 3242 | 23 | 0 | 3242/3242 issues pass the rule | 1 | Total number of issues present in this Open-Source Project is: 3242. Total number of missing issues present in this Open-Source Project is: 0. Total number of sprints present in this Open-Source Project is: 23. Total number of missing sprint IDs present in this Open-Source Project is: 2032.
MDL | 63273 | 269 | 1 | 63272/63273 issues pass the rule 1/63273 issues fail the rule | 0 | Total number of issues present in this Open-Source Project is: 63273. Total number of missing issues present in this Open-Source Project is: 1. Total number of sprints present in this Open-Source Project is: 269. Total number of missing sprint IDs present in this Open-Source Project is: 60540.
DNN | 1874 | 103 | 0 | 1874/1874 issues pass the rule | 1 | Total number of issues present in this Open-Source Project is: 1874. Total number of missing issues present in this Open-Source Project is: 0. Total number of sprints present in this Open-Source Project is: 103. Total number of missing sprint IDs present in this Open-Source Project is: 246.
Mesos | 1365 | 70 | 0 | 1365/1365 issues pass the rule | 1 | Total number of issues present in this Open-Source Project is: 1365. Total number of missing issues present in this Open-Source Project is: 0. Total number of sprints present in this Open-Source Project is: 70. Total number of missing sprint IDs present in this Open-Source Project is: 286.
Mule | 1278 | 104 | 0 | 1278/1278 issues pass the rule | 1 | Total number of issues present in this Open-Source Project is: 1278. Total number of missing issues present in this Open-Source Project is: 0. Total number of sprints present in this Open-Source Project is: 104. Total number of missing sprint IDs present in this Open-Source Project is: 120.
Nexus | 1037 | 70 | 0 | 1037/1037 issues pass the rule | 1 | Total number of issues present in this Open-Source Project is: 1037. Total number of missing issues present in this Open-Source Project is: 0. Total number of sprints present in this Open-Source Project is: 70. Total number of missing sprint IDs present in this Open-Source Project is: 404.
Timob | 1853 | 63 | 0 | 1853/1853 issues pass the rule | 1 | Total number of issues present in this Open-Source Project is: 1853. Total number of missing issues present in this Open-Source Project is: 0. Total number of sprints present in this Open-Source Project is: 63. Total number of missing sprint IDs present in this Open-Source Project is: 1574. Most of the sprints have low number of issues resolved in them. The team perhaps did not correctly mapped the issues into the sprint they were completed in Jira, and perhaps the issues actually were resolved in one of these valid 63 sprints. This is another remark for future, that agile teams need to use Jira correctly and map out all activities related to the issues in order for us to have clearer data and better insights.
R35 - Scrum Sprints have a starting time. There should be timestamp indicating the sprints kick-off.
Project Name | Sprint Sample Value | Total Sprints | Sprints having no Start Date | Percentage (Sprint Unit) | Binary Output | Comments
XD | Sprint 68 | 66 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Apstud | 2012 Sprint 15 | 34 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Tistud | 2012 Sprint 18 | 59 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Mobile | "[’com.atlassian.greenhopper.service.sprint.Sprint@40c6b8aa[id=237,rapidViewId=126,state=ACTIVE,name=Moodle 3.9 - Moppies Kanban,startDate=2019-09-15T13:49:00.000Z,endDate=2019-10-31T14:49:00.000Z,completeDate=<null>,sequence=237,goal=<null>]’]" | 23 | 0 | 23/23 sprints pass the rule | 1 | There are 23 sprints in this project, and for each of them we have the start date. However, there are many issues that do not belong to any sprints, which in the data is reflected as the NaN sprint.
MDL | "['com.atlassian.greenhopper.service.sprint.Sprint@69955a6a[id=246,rapidViewId=115,state=CLOSED,name=Internationals - 3.8 Alpha,startDate=2019-10-08T02:30:06.385Z,endDate=2019-10-15T02:30:00.000Z,completeDate=2019-12-02T05:32:44.130Z,sequence=246,goal=Feature completion]']" | 269 | 0 | 269/269 sprints pass the rule | 1 | There is no sprint that has a null value for the start date. Also checked manually for all sprints' start dates and all 269 have a timestamp indicating the start date of the given sprint.
DNN | Sprint 2; Content 8.1.0 - Sprint 3 | 103 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Mesos | Mesosphere Sprint 34 | 70 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Mule | startDate=2016-04-27T11:27:32.496-05:00 | 104 | 1 startDate=<null> | 103/104 spritns pass the rule 1/104 spritns fails the rule | 0 | There are 104 sprints, out of which 103 have a valid timestamp indicating the beginning of the sprint. However, 1 sprint does not have a valid start date. There are also 47 issues that belong to no sprints, and this value is reflected as NaN in the sprint field.
Nexus | Sprint 68 - Föhn | 70 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Timob | 2012 Sprint 20 | 63 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
R36 - Scrum Sprints have a completion time. There should be timestamp indicating the sprints completion/resolution.
Project Name | Sprint Sample Value | Total Sprints | Sprints having no End Date | Percentage (Sprint Unit) | Binary Output | Comments
XD | Sprint 68 | 66 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Apstud | 2012 Sprint 15 | 34 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Tistud | 2012 Sprint 18 | 59 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Mobile | "[’com.atlassian.greenhopper.service.sprint.Sprint@40c6b8aa[id=237,rapidViewId=126,state=ACTIVE,name=Moodle 3.9 - Moppies Kanban,startDate=2019-09-15T13:49:00.000Z,endDate=2019-10-31T14:49:00.000Z,completeDate=<null>,sequence=237,goal=<null>]’]" | 23 | 0 | 23/23 sprints pass the rule | 1 | Sample end date for this project: endDate=2018-11-06T06:39:00.000Z,completeDate=2019-02-07T11:09:45.209Z. There are 23 sprints in this project, and for each of them we have the end date and completion date. However, there are many issues that do not belong to any sprints, which in the data is reflected as the NaN sprint.
MDL | "['com.atlassian.greenhopper.service.sprint.Sprint@69955a6a[id=246,rapidViewId=115,state=CLOSED,name=Internationals - 3.8 Alpha,startDate=2019-10-08T02:30:06.385Z,endDate=2019-10-15T02:30:00.000Z,completeDate=2019-12-02T05:32:44.130Z,sequence=246,goal=Feature completion]']" | 269 | 0 | 269/269 sprints pass the rule | 1 | There is no sprint that has a null value for the start date. Also checked manually for all sprints' start dates and all 269 have a timestamp indicating the start date of the given sprint.
DNN | Sprint 2; Content 8.1.0 - Sprint 3 | 103 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Mesos | Mesosphere Sprint 34 | 70 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Mule | startDate=2016-04-27T11:27:32.496-05:00 | 104 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information. We only have information about start date of the sprint for this project.
Nexus | Sprint 68 - Föhn | 70 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
Timob | 2012 Sprint 20 | 63 | N/A | N/A | N/A | This rule is not applicable for this project, because we do not have the needed information.
R37 - There should be a minimum of one issue, representing a Sprint Backlog Item, per each Sprint.
Project Name | Total Issues | Total Sprints | Min PBIs per Sprint | Max PBIs per Sprint | Sprints having 0 PBIS | Percentage (Issues Unit) | Binary Output | Comments
XD | 3152 | 66 | 1 | 87 | 0 | 66/66 sprints pass the rule | 1 | N/A
Apstud | 825 | 34 | 1 | 35 | 0 | 34/34 sprints pass the rule | 1 | N/A
Tistud | 2826 | 59 | 10 | 67 | 0 | 59/59 sprints pass the rule | 1 | N/A
Mobile | 3242 | 23 | 1 | 180 | 0 | 23/23 sprints pass the rule | 1 | N/A
MDL | 63273 | 269 | 1 | 129 | 0 | 269/269 sprints pass the rule | 1
DNN | 1874 | 103 | 1 | 91 | 0 | 103/103 sprints pass the rule | 1 | There are many sprints having only 1 issue completed in them! 21/103 sprints have only 1 issue completed during the sprint. This project generally has low PBIs per sprints.
Mesos | 1365 | 70 | 1 | 69 | 0 | 70/70 sprints pass the rule | 1 | N/A
Mule | 1278 | 104 | 1 | 43 | 0 | 104/104 sprints pass the rule | 1
Nexus | 1037 | 70 | 1 | 42 | 0 | 70/70 sprints pass the rule | 1 | This project generally has low PBIs per sprints.
Timob | 1853 | 63 | 1 | 37 | 0 | 63/63 sprints pass the rule | 1 | This project generally has low PBIs per sprints. There are 24 sprints that only have 1 issue resolved in them!
R38 - There should be timestamp indicating the issue development kick-off.
Project Name | Total Issues | Issues having no Start Date | Percentage (Issues Unit) | Binary Output | Comments
XD | 3152 | 0 | 3152/3152 issues pass the rule | 1 | Total number of issues in the Open-Source Project are: 3152. Total number of unique issues (excluding nan) in the Open-Source Project are: 3152. There are: 0 issue duplicates! In case of duplicate issues, the duplicates will be removed! However, this step was already performed in the data cleaning part. Total number of issues having no created date is: 0.
Apstud | 825 | 0 | 825/825 issues pass the rule | 1 | Total number of issues in the Open-Source Project are: 825. There are: 0 issue duplicates! Total number of missing values in the *key* column in the Open-Source Project: 0. Total number of issues having no created date is: 0.
Tistud | 2826 | 0 | 2826/2826 issues pass the rule | 1 | Total number of issues in the Open-Source Project are: 2826. There are: 0 issue duplicates! Total number of missing values in the *key* column in the Open-Source Project: 0. Total number of issues having no created date is: 0.
Mobile | 3242 | 0 | 3242/3242 issues pass the rule | 1 | Total number of issues in the Open-Source Project are: 3242. Total number of unique issues (excluding nan) in the Open-Source Project are: 3242. Total number of missing values in the *key* column in the Open-Source Project: 0. Total number of issues having no created date is: 0.
MDL | 63273 | 0 | 63273/63273 issues pass the rule | 1 | Total number of issues in the Open-Source Project are: 63273. Total number of missing values in the *key* column in the Open-Source Project: 1. Total number of issues having no created date is: 0. Even the 1 issue which does not have an ID/name, it has been created and records a creation date.
DNN | 1874 | 0 | 1874/1874 issues pass the rule | 1 | Total number of issues in the Open-Source Project are: 1874. Total number of unique issues (excluding nan) in the Open-Source Project are: 1874. Total number of missing values in the *key* column in the Open-Source Project: 0. Total number of issues having no created date is: 0.
Mesos | 1365 | 0 | 1365/1365 issues pass the rule | 1 | Total number of issues having no created date is: 0.
Mule | 1278 | 0 | 1278/1278 issues pass the rule | 1 | Total number of issues in the Open-Source Project are: 1278. Total number of missing values in the *key* column in the Open-Source Project: 0. Total number of issues having no created date is: 0.
Nexus | 1037 | 0 | 1037/1037 issues pass the rule | 1 | Total number of issues in the Open-Source Project are: 1037. Total number of missing values in the *key* column in the Open-Source Project: 0. Total number of issues having no created date is: 0.
Timob | 1853 | 0 | 1853/1853 issues pass the rule | 1 | Total number of issues in the Open-Source Project are: 1853. Total number of missing values in the *key* column in the Open-Source Project: 0. Total number of issues having no created date is: 0.
R39 - There should be timestamp indicating the issue development completion.
Project Name | Total Issues | Issues having no End Date | Percentage (Issues Unit) | Binary Output | Comments
XD | 3152 | 574 | 2578/3152 issues pass the rule 574/3152 issues fail the rule | 0 | Total number of issues in the Open-Source Project are: 3152. There are: 0 issue duplicates! Total number of missing values in the *key* column in the Open-Source Project: 0. Total number of issues having no end date is: 574.
Apstud | 825 | 237 | 588/825 issues pass the rule 237/825 issues fail the rule | 0 | Total number of issues in the Open-Source Project are: 825. There are: 0 issue duplicates! Total number of missing values in the *key* column in the Open-Source Project: 0. Total number of issues having no end date is: 237.
Tistud | 2826 | 198 | 2628/2826 issues pass the rule 198/2826 issues fail the rule | 0 | Total number of issues in the Open-Source Project are: 2826. There are: 0 issue duplicates! Total number of issues having no end date is: 198.
Mobile | 3242 | 359 | 2883/3242 issues pass the rule 359/3242 issues fail the rule | 0 | Total number of issues having no end date is: 359.
MDL | 63273 | 10285 | 52988/63273 issues pass the rule 10285/63273 issues fail the rule | 0 | Total number of issues in the Open-Source Project are: 63273. Total number of missing values in the *key* column in the Open-Source Project: 1. Total number of issues having no end date is: 10285.
DNN | 1874 | 104 | 1770/1874 issues pass the rule 104/1874 issues fail the rule | 0 | Total number of issues in the Open-Source Project are: 1874. Total number of unique issues (excluding nan) in the Open-Source Project are: 1874. Total number of issues having no end date is: 104.
Mesos | 1365 | 277 | 1088/1365 issues pass the rule 277/1365 issues fail the rule | 0 | Total number of issues having no end date is: 277.
Mule | 1278 | 78 | 1209/1287 issues pass the rule 78/1287 issues fail the rule | 0 | Total number of issues in the Open-Source Project are: 1278. Total number of issues having no end date is: 78.
Nexus | 1037 | 42 | 995/1037 issues pass the rule 42/1037 issues fail the rule | 0 | Total number of issues in the Open-Source Project are: 1037 Total number of missing values in the *key* column in the Open-Source Project: 0. Total number of issues having no end date is: 42. This project has the lowest number of incomplete issues, proportionally to the number of total issues among all projects
Timob | 1853 | 174 | 1679/1835 issues pass the rule 174/1853 issues fail the rule | 0 | Total number of issues in the Open-Source Project are: 1853. Total number of issues having no end date is: 174.